QM 7363-01  Capstone Project Plan  ·  Version 2

Agentic Risk Analyst

Roles, responsibilities, and task sequence for a five-person team

| Field | Detail |
| --- | --- |
| Version | v2, September 27, 2026. Supersedes v1 of September 20. |
| Window | September 28 to December 7, 2026 (10 weeks). Instructor deadline is mid-December. |
| Team | Mark (lead), Jessica, Said Shoaib, Enock, Mouzam Younas. |
| Data | Mouzam's firm-year panel, final_panel. 83,726 firm-years and 12,275 firms, FY2011 to FY2022, 18 features plus a recovered CFsale. Modelling sample is the 42,728 audited firm-years. |
| Deliverable | A working application that uses agentic AI to assess financial misstatement risk. |

What changed from v1 Mouzam's panel replaced FinalCleanedData.csv, which moved the period from FY2004-2019 to FY2011-2022, supplied a clean firm identifier, recovered cash flow to sales, and eliminated the Excel error problem. The identifier is the consequential one: 10-K narrative retrieval is viable again, so it returns to the plan as a second evidence source. Task 1.1 from v1 is deleted because the cleaning it described is already done. The schedule slides one week to protect its buffer rather than compressing.

# 1. What we are building

GA-TAN produces a posterior probability. A probability is not an assessment, because it does not say what was examined, what pointed the other way, or what should be checked next.

The Agentic Risk Analyst replaces the fixed pipeline with a language model that has tools. The tools are deterministic queries: pull a firm's history, run the risk model, retrieve its nearest peers and their outcomes, measure how far a ratio sits from the firm's own norm, run a counterfactual, and retrieve the relevant passage of its 10-K. The agent decides which queries to run for the firm in front of it, follows up when a result is ambiguous, and returns an assessment together with the complete record of what it called and what came back.

That record is the product. Every claim in the assessment maps to a tool result, and the whole investigation can be replayed. A claim that maps to nothing is blocked before display rather than flagged.

The improvement claim, stated plainly The source paper scores a firm. This investigates one, drawing on both the financial panel and the firm's own filings, and leaves a reproducible trail of the investigation. That is what we are testing and what the report will argue.

# 2. The data we are now working from

Mouzam rebuilt the panel from five Compustat and WRDS extracts, keyed one-to-one on gvkey and datadate, validated against the WRDS Financial Ratios Suite. It supersedes FinalCleanedData.csv for all purposes.

| Property | Value |
| --- | --- |
| Size | 83,726 firm-years, 12,275 firms, FY2011 to FY2022 |
| Modelling sample | 42,728 firm-years, 6,187 firms, 4.70 percent adverse |
| Features | 18, plus CFsale computed as oibdp / sale on 88 percent of rows |
| Identifiers | gvkey (clean), conm, cusip and tic (need re-export, see task 0.6) |
| Industry | SIC on every row, with the fill order recorded in SIC_SOURCE |
| Timing discipline | INFO_DATE = fiscal year-end plus three months |
| Winsorizing | 1st and 99th percentile within each fiscal year, raw columns kept |
| Cross-validation | 87.9 percent of the professor's FY2011-2019 rows match on name and year, and the labels agree on 99.96 percent of those |

## 2.1 The label, and the trap in it

The target is auopic, the auditor's opinion on internal control over financial reporting. Mouzam's notes list identifying a label source as an open item. It is already in the panel, at column 72, populated on 83,537 rows.

| Code | Rows | Meaning |
| --- | --- | --- |
| 0 | 40,802 | No auditor attestation on internal controls. Smaller filers are exempt under SOX 404(b). These firms were never assessed. |
| 1 | 40,719 | Assessed and effective. This is the true negative. |
| 2 | 2,009 | Adverse opinion. A material weakness. This is the positive class. |
| 3 and 4 | 7 | Rare. Exclude. |

Code 0 must be excluded, and it is 48.8 percent of the panel. Those rows carry a label that means unknown, not clean. Filter to codes 1 and 2 and the modelling sample is 42,728 rows at a 4.70 percent adverse rate. Treat 0 as clean and you get 83,537 rows at 2.41 percent, half of them mislabelled. The professor's original file contained no code 0, which means it had already been filtered this way.

## 2.2 Baseline results, for reference

Training on FY2011 through 2017, testing on FY2018 through 2022, audited rows only. These are the numbers the model engineer should expect to reproduce or beat.

| Features | ROC | PR-AUC | Top 5% prec. | Lift |
| --- | --- | --- | --- | --- |
| 18 features plus CFsale | .751 | .161 | 20.8% | 3.8x |
| Plus 2-digit SIC | .756 | .161 | 20.4% | 3.8x |
| Plus prior-year opinion | .826 | .329 | 41.6% | 7.7x |

# 3. The five roles

Every role has a primary and an assistant. The assistant is not a spare pair of hands. They review the primary's work before it is handed off, they own named subtasks of their own, and they take over if the primary is unavailable. Each person carries one primary role and one assistant role.

| Role | Primary | Assistant | Hands off |
| --- | --- | --- | --- |
| R1 Team Lead | Mark | Said Shoaib | Report, slides, demo |
| R2 Data and Model | Jessica | Enock | score_firm() and a frozen model artifact |
| R3 Tool Layer | Said Shoaib | Mouzam | Tool module and test suite |
| R4 Agent | Enock | Jessica | Agent module and trace format |
| R5 Application and Evaluation | Mouzam Younas | Mark | Application and results tables |

## R1  Team Lead.  Primary Mark, assistant Said Shoaib.

Mark runs the schedule and the twice-weekly meeting, owns the instructor relationship and the decision log, assembles the final report, builds the presentation, and arbitrates scope. Said Shoaib keeps the decision log current during meetings and drafts the instructor-facing one-pagers, so neither depends on one person being in the room.

## R2  Data and Model.  Primary Jessica, assistant Enock.

Jessica applies the auopic filter, settles the label-timing question, builds the feature table including CFsale, trains and calibrates the risk model, and writes the model card. Enock owns the temporal split and the second-seed sensitivity re-run in task 6.6, so model results are reproduced by someone other than the person who produced them.

## R3  Tool Layer.  Primary Said Shoaib, assistant Mouzam.

Said Shoaib builds the nine query functions, each deterministic and each returning a source string that resolves to specific rows and columns. Mouzam owns the unit test suite in task 2.4 and the identifier re-export in task 0.6. Testing tools against the panel he built himself is the best use of what he already knows, and writing tests against someone else's functions catches more than testing your own.

## R4  Agent.  Primary Enock, assistant Jessica.

Enock writes the tool schemas, the agent loop, the system prompt and its constraints, the call budget, the output contract, and the verification step that blocks unmatched claims. Jessica owns the trace logger in task 3.3 and trace replay in task 6.5.

## R5  Application and Evaluation.  Primary Mouzam Younas, assistant Mark.

Mouzam builds the Streamlit application and the evaluation harness. Mark owns the reproducibility check in task 7.2 and the demo, and works the language-model head-to-head in task 6.3 alongside Mouzam.

# 4. The sequencing problem, and how we solve it

Read naively, this project is a chain. The model must exist before tools can wrap it, tools must exist before the agent can call them, and the agent must exist before anything can be evaluated. A chain means R4 and R5 sit idle for a month and then everything lands in the last three weeks.

The fix is to agree the interface before anyone builds behind it. In week one, Jessica, Said Shoaib and Enock write the exact signature and return shape of all nine tools. Said Shoaib then builds stub versions that return correctly shaped fake data on day two. Enock builds the entire agent against those stubs while Jessica is still training the model. Real implementations replace stubs one at a time without the agent changing.

Week one deliverable, before any modelling A written tool contract: nine function signatures, their arguments, their return schema, and the shape of the source string. Nobody starts real implementation until all five members have signed off. This single document is what lets four people work in parallel for a month.

## 4.1 The narrative track, and why it is gated

The panel carries gvkey, which resolves to a CIK, which reaches the firm's actual filings on EDGAR. That restores the evidence source the original project concept was built around and that v1 had to abandon.

It is gated deliberately. Resolving identifiers to CIK will not cover every firm, historical ticker changes and delisted companies will cause misses, and we will not know the coverage rate until task 2.5 measures it. The narrative tools therefore sit in phase 2 and phase 3, behind a coverage gate at task 5.7. If coverage is high the agent gains a second evidence source. If it is low the narrative layer is documented as covering a stated subset. Either way the application works, because nothing upstream depends on it.

# 5. Task sequence

Ten weeks, September 28 to December 7. Rows shaded green are new in v2.

## Phase 0.  Contract and setup  (week 1, Sept 28 to Oct 4)

| # | Owner | Task | Blocks |
| --- | --- | --- | --- |
| 0.1 | All | Agree the tool contract: nine signatures, arguments, return schema, source-string format. Written down and signed off. | Everything |
| 0.2 | Mark | Repository, shared environment, pinned dependencies, meeting cadence, decision log opened. | All build work |
| 0.3 | Said Shoaib | Stub implementations of all nine tools returning correctly shaped fake data. | 3.x |
| 0.4 | Mark | Send the instructor a one-page summary of this plan, including the auopic code 0 finding. |  |
| 0.5 | Mouzam | Choose the two language models for the head-to-head. Obtain and test API access. | 4.1 |
| 0.6 | Mouzam | Re-export cusip and tic as text. cusip currently loses leading zeros on about 4,400 rows and holds floating-point garbage on 1,344; tic is absent from the file. | 2.5 |

## Phase 1.  Parallel build  (weeks 2 to 4, Oct 5 to Oct 25)

Four workstreams run at once. None waits on another because everything targets the contract.

| # | Owner | Task | Depends on |
| --- | --- | --- | --- |
| 1.1 | Jessica | Apply the label filter. Keep auopic 1 and 2, exclude 0, 3 and 4. Document the exclusion and its effect on the base rate. | 0.2 |
| 1.2 | Jessica | Settle label timing using INFO_DATE: explain year t or predict year t+1. Decision logged. | 1.1 |
| 1.3 | Jessica | Feature table including CFsale = oibdp / sale. Decide how INV_TURN and DPR are handled given their structural missingness. | 1.2 |
| 1.4 | Enock | Temporal split, fixed and documented. | 1.2 |
| 1.5 | Jessica | Train the risk model against a logistic baseline. Calibration curve. Target: at or above ROC .826. | 1.3, 1.4 |
| 1.6 | Jessica | Freeze model v1. Write the model card. Expose score_firm(). | 1.5 |
| 2.1 | Said Shoaib | Implement get_firm_history, get_control_history, get_percentile, get_deviation. | 0.1 |
| 2.2 | Said Shoaib | Implement get_peer_cohort and get_cohort_rate. Peer retrieval in standardised space, with SIC available as a cohort key. | 2.1 |
| 2.3 | Said Shoaib | Implement get_industry_context using SIC. | 2.2 |
| 2.4 | Mouzam | Unit tests. Every tool checked against three hand-verified firms. | 2.3 |
| 2.5 | Said Shoaib | Resolve gvkey to CIK across the panel. Report the coverage rate. This number decides the narrative track. | 0.6 |
| 3.1 | Enock | Tool schemas and the agent loop against stubs. Call budget enforced. | 0.3 |
| 3.2 | Enock | System prompt and output contract: assessment, evidence, contradictory evidence, uncertainty, recommended checks. | 3.1 |
| 3.3 | Jessica | Trace logger. Every call, argument and return persisted in replayable form. | 3.1 |
| 4.1 | Mouzam | Streamlit shell. Firm and year selection, results pane, trace viewer. | 0.5 |
| 4.2 | Mouzam | Evaluation design written: what claim resolution means, how traces are scored, how adversarial cases are built. | 0.1 |

## Phase 2.  Integration  (weeks 5 to 6, Oct 26 to Nov 8)

| # | Owner | Task | Depends on |
| --- | --- | --- | --- |
| 5.1 | Said Shoaib | Wrap the frozen model as score_firm and run_counterfactual. Swap out the last stubs. | 1.6, 2.4 |
| 5.2 | Enock | Point the agent at real tools. First complete end-to-end assessment on one firm. | 5.1, 3.3 |
| 5.3 | Enock | Verification step: match every numeric claim to a tool result, block what does not match. | 5.2 |
| 5.4 | Mouzam | Wire the application to the agent. Trace viewer renders real traces. | 5.2, 4.1 |
| 5.5 | Said Shoaib | EDGAR retrieval for the resolved subset. Download and parse Item 7 and Item 9A. | 2.5 |
| 5.6 | Said Shoaib | Implement get_filing_excerpt, the ninth tool. Returns a passage plus a citation to filing, section and paragraph. | 5.5 |
| 5.7 | All | Coverage gate. Review the CIK resolution rate and decide whether the narrative tool ships to all firms, to a stated subset, or is deferred to future work. | 2.5, 5.6 |
| 5.8 | Mark | Internal demo to the whole team. Midpoint check-in with the instructor. | 5.4 |
| 5.9 | All | Freeze the prompt and the output contract. No further changes before evaluation. | 5.8 |

## Phase 3.  Hardening  (weeks 7 to 8, Nov 9 to Nov 22)

| # | Owner | Task | Depends on |
| --- | --- | --- | --- |
| 6.1 | Mouzam | Build 30 adversarial cases: contradictory signals, sparse histories, scores near the threshold. | 5.9 |
| 6.2 | Mouzam | Run the harness across 200 or more assessments. Report claim resolution rate and block rate. | 6.1 |
| 6.3 | Mark | Head-to-head between the two language models on the identical case set. | 6.2 |
| 6.4 | Enock | Fix failures the harness surfaces, or document them as known limits. | 6.2 |
| 6.5 | Jessica | Trace replay: re-running a stored trace reproduces the same tool returns. | 6.2 |
| 6.6 | Enock | Sensitivity check: rerun the model with a second seed and confirm the results hold. | 1.6 |
| 6.7 | Mouzam | If the narrative tool shipped, measure passage-citation accuracy separately from numeric claim resolution. Text claims need their own check. | 5.7 |

## Phase 4.  Close  (weeks 9 and 10, Nov 23 to Dec 7)

| # | Owner | Task | Depends on |
| --- | --- | --- | --- |
| 7.1 | All | Code freeze. No new features. | Phase 3 |
| 7.2 | Mark | Reproducibility check. Clone the repository on a clean machine and regenerate every reported number. | 7.1 |
| 7.3 | Mark | Draft the final report. Each owner writes their own methods section. | 7.1 |
| 7.4 | Mouzam | Record the backup demo. | 7.1 |
| 7.5 | Mark | Build slides. Rehearse the demo twice. | 7.3 |
| 7.6 | All | Proofread, submit by December 7. | 7.5 |

# 6. The nine tools

Agreed in week one. The first eight are built in phase 1, the ninth in phase 2 behind the coverage gate. Each returns structured data plus a source string that resolves to a specific location in the data or a specific passage in a filing.

| Tool | Returns |
| --- | --- |
| get_firm_history | All fiscal years on record for a firm, with ratios and control opinions |
| get_control_history | The years in which a firm received an adverse opinion |
| score_firm | Model probability for a firm-year, plus its rank among firms that year |
| get_percentile | Where a firm's value on one variable sits within that fiscal year |
| get_deviation | How far a value sits from that firm's own historical median |
| get_peer_cohort | The k nearest firms in standardised financial space and their observed outcome rate |
| get_cohort_rate | The observed adverse rate for a named slice, such as a size decile |
| get_industry_context | The adverse rate and typical ratio ranges for the firm's SIC group |
| get_filing_excerpt | A passage from Item 7 or Item 9A of the firm's 10-K, with filing, section and paragraph cited |

# 7. Definition of done

| Role | Done means |
| --- | --- |
| R1 Mark and Said Shoaib | Report submitted, demo rehearsed, every reported number regenerated from a clean clone, decision log complete and current. |
| R2 Jessica and Enock | Model frozen with a model card. The label filter and timing decision are documented. A teammate rebuilds the modelling table from the panel with one command, and the second-seed run confirms the results. |
| R3 Said Shoaib and Mouzam | All shipped tools implemented, unit tested against hand-verified firms, every return carrying a resolvable source string, and the CIK coverage rate reported. |
| R4 Enock and Jessica | Agent runs inside its call budget, emits the agreed output schema, logs a replayable trace, and blocks every claim that does not match a tool result. |
| R5 Mouzam and Mark | Application runs end to end on a clean machine from the README. Harness results and the model head-to-head are tabulated. |

# 8. The four things most likely to go wrong

- The contract slips past week one. Everything downstream is then serial and the project lands in the final fortnight. If the contract is not signed off by October 4, that is the escalation trigger.

- Someone models on auopic without filtering code 0. Half the sample then carries a label meaning unknown, the base rate halves, and every result is quietly wrong. Task 1.1 exists to prevent this and its output is reviewed by Enock.

- The agent wanders and burns its call budget without reaching an answer. Cap the calls, log every one, and treat budget exhaustion as a reportable failure rather than an error to hide.

- Tool correctness is assumed rather than tested. A tool that returns a plausible wrong number produces an assessment that is confidently wrong and passes verification. Task 2.4 is not optional.

# 9. Note on the schedule

This version runs to December 7 rather than November 30. The extra week preserves the full ten-week plan instead of compressing it into nine, which was the alternative once the original start date passed.

That trade has a cost worth naming. The November 30 target existed to clear the decks before finals. December 7 eats one week of that margin. The buffer to the instructor's mid-December deadline still holds, and if the team finishes phase 3 on time in the week of November 22, phase 4 can be pulled forward and the original date recovered.